## definizioni
Project Earned Value Analysis
Project Earned Value Analysis measures the health of a project by looking at cost information and schedule information concurrently. It tells you whether the project is on schedule and on budget, as well as whether the project is on budget for the amount of work done so far.
Metric | Abbrev. | Descrizione | Formula/Value
Budget at Completion | BAC | Baseline cost for 100% of project. | N/A
Actual Cost | AC | Total costs actually incurred so far. | N/A
Planned Value | PV | The budget for the physical work scheduled to be completed by the end of the time period. | N/A
Earned Value | EV | Amount of budget earned so far based on physical work accomplished, without reference to actual costs. | PV to date * RP (Rate of Performance)
Cost Variance | CV | Measure of cost overrun. The difference between the budget for the work actually done so far and the actual costs so far. | EV - AC
Cost Performance Index | CPI | Cost efficiency ratio. A CPI of 1.00 means that the costs so far are exactly the same as the budget for work actually done so far. | EV/AC
Schedule Variance | SV | Measure of schedule slippage. The difference between the budget for the work actually done so far and the budgeted cost of work scheduled. | EV - PV
Schedule Performance Index | SPI | The schedule efficiency ratio. An SPI of 1.0 means that the project is exactly on schedule. | EV/PV
Estimate to Completion | ETC | The expected additional cost to complete. | BAC - AC
Estimate at Completion | EAC | Expected total cost based on the current cost efficiency ratio. | BAC/CPI
Variance at Completion | VAC | Estimated cost overrun at the end of project. | BAC - EAC
Status |  | Average of CPI & SPI. | (CPI+SPI)/2
|  | GREEN = On track | >1.0
|  | YELLOW = Slightly behind schedule or budget | >0.85
|  | RED = Needs immediate attention | >0.65
|  | BLACK = Killed or Restore | <0.65

## tabella
Project Earned Value Analysis
Esistere | RAD | SDD | Report I | TP/TCS | Report II | ODD | SC (Prima parte) | Report III | SC (Totale) | Testing | Manuali | Report III
Metric | 2023-11-22 | 2023-12-04 | 2023-12-05 | 2023-12-16 | 2023-12-16 | 2024-01-01 | 2024-01-03 | 2024-01-03 | 2024-01-20 | 2024-01-20 | 2024-01-20 | 2024-01-20
Budget at Completion (BAC) | 1450 | 560 | 2010 | 490 | 2500 | 700 | 720 | 3920 | 2380 | 1190 | 140 | 6910
Earned Value (EV) | 1450 | 560 | 2010 | 490 | 2500 | 700 | 720 | 3920 | 2380 | 1190 | 140 | 6910
Actual Cost (AC) | 1510 | 560 | 2070 | 390 | 2460 | 700 | 720 | 3880 | 2375 | 1000 | 140 | 6675
Planned Value (PV) | 1450 | 560 | 2010 | 490 | 2500 | 700 | 720 | 3920 | 2380 | 1190 | 140 | 6910
%Progress (RP) | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Cost Variance (CV) | -60 | 0 | -60 | 100 | 40 | 0 | 0 | 40 | 5 | 190 | 0 | 235
Schedule Variance (SV) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cost Performance Index (CPI) | 0.96026 | 1 | 0.97101 | 1.2564 | 1.0163 | 1 | 1 | 1.0103 | 100.2% | 119% | 100% | 103.5%
Schedule Performance Index (SPI) | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Estimate to Completion (ETC) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Estimate at Completion (EAC) | 1510 | 560 | 2070 | 390 | 2460 | 700 | 720 | 3880 | 2375 | 1000 | 140 | 6675
Variance at Completion (VAC) | -60 | 0 | -60 | 100 | 40 | 0 | 0 | 40 | 5 | 190 | 0 | 235
Average Index | 0.98013 | 1 | 0.98551 | 1.1282 | 1.0081 | 1 | 1 | 1.0052 | 1.0011 | 1.095 | 1 | 1.0176
Stato | YELLOW | GREEN | YELLOW | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN | GREEN
Note